## Slide 1
Basin Scale Resilience Initiative for Ethiopia (BaSRINET) Project
BaSRINET Project Update
April 29/2025

## Slide 2: Content
Brief Project Description
Progress Update
Key Areas of Improvement

## Slide 3: 1. Project Description
IWRM Issues to Address:
Coordination and Sectorial Integration
WR information/data management
Institutional Capacities
Livelihood Options
Climate Change
Access to Water
Energy Access
Flooding
Conflicts
Project Goal:
contribute to the resilience of pastoral and agro-pastoral communities´ and build sustainable livelihoods water in Awash and Wabi- Shebele basins|
BAsin Scale Resilience INitiative for
EThiopia (BA.S.R.IN.ET)

## Slide 4: 1. Project Description
BA.S.R.IN.ET Objective
To ensure well-organized, accurate and comprehensive hydrological basin information system;
To ensure adequate supply of water for domestic and agricultural needs
To manage selected vulnerable watersheds and protect buffer zones
To strengthen the technical, managerial and regulatory capacities of MoWE/BAOs and Regions
To develop small-scale renewable energy sources for water abstraction and other economic uses

## Slide 5: 1. ….. Project Description
Project Basins:
Awash Basin
Wabi-shebele Basin
Denakil Basin (EU)
Beneficiary
Direct 280,000 pastoral and agro-pastoral communities in Awash and Wabi-Shebele Basin
Indirect 870,000 people of the target basins

## Slide 6: 1. ….. Project Description

## Slide 7: 1. ….. Project Description
Implementation Period

## Slide 8: 1. Project Description
€ 49.5 Million
Total Budget
Donor:
Italian Agency for Development Cooperation |AICS|
European Union |EU|
Executing Agency:
Ministry of Water and Energy |MoWE|
Italian Agency for Development Cooperation | AICS |
Funds:
€ 24 Mln Soft Loan to MoWE
€ 7.5 Mln Grant to MoWE
€ 31.5 Mln total project cost (MoWE)
Release
€ 2.5 Million

## Slide 9: 3. Progress Update ----- Preparatory
Project submission _ 2021
Agreement … March 2023
Create Bank Accounts and Assigning Person in charge _ Nov 2023
Launching _ Mar 2024
Review BASRINET Plan of Action _ Sept 2024
Sign MoU MoWE – AICS (EU) _ Nov 2024
BaSRINET Project Staffing _ Dec 2024
BASRINET Project Staff on-boarding _ Jan 2025
Detailing the 2024/25 Plan and Consultations (MoWE)
Quick Assessment and Inception (MoWE_AICS_EU), Quick assessment (EU) _ Jan 2025

## Slide 10: 3. Progress Update ----- Main Tasks
The 2025 – 2027 Plan of Action for SC Endorsement
Terms of references: Five
- Seedling GLI support
- Hydrology stations including installations _ # 15
- Water supply and energy provisions planning and design
- GIS based web-portal establishment (design and installation)
- Kelafo Flood Control Implementation
3. Procurement:
- Procurement plan endorsed
- Office facility (PC and Furniture)
- Field car

## Slide 11: 3. Progress Update ----- Main Tasks
4. Capacity building: Training (Till Dec 2024) _ by IFAD
- Procurement and contract administration (May 2025)
- Project Management including M&E and Finance (June 2025)
- MoWE _ IWRM Capacity Development Strategy
- Project website and communication
- Harmonized IWRM Project Plan _ BRIGHT, BASRINET, FMP, HoAGW4R

## Slide 12: 3. Key areas of Improvement
Endorsement of the BASRINET Plan of Action by SC.
Procurement of office supplies and staffing
Project resources harmonization
Assessment, Bidding and procurement

## Slide 13
Thank You